## Sheet1
Days to Launch | Activity | Goal
14 | Launch badge landing page on website | Create resources
14 | Update cert requirements and web pages as necessary | Create resources
12 | "Badging coming soon" mention in newsletter and on social media | Building buzz
12 | Don't forget to message sponsors/stakeholders so they know what's coming, too | Building buzz
9 | Social media post 2: How to earn a badge | Building buzz
6 | Social media post 3: Benefits of sharing a badge | Building buzz
4 | Badging webinar explaining the program and benefits | Building buzz
3 | Update "congratulations" auto-response to include badge information | Prepare earners to engage
3 | Send "pre-notification message" to retroactive badge earners | Prepare earners to engage
0 | Publish press release | Expand awareness
0 | Issue retroactive badges: badge notification emails delivered | Launch!
Ongoing | Begin issuing real-time badges | Launch!
Days Post-Launch | Activity | Goal
Ongoing (daily) | Like and comment on earner shares | Expand visibility
Ongoing (1-2x/month) | Re-share on LinkedIn (with earner's permission) | Expand visibility
21 | Evaluate initial engagement data and make necessary updates | Improve process and program
21 | Identify badge "champions" to be used in marketing/comms | Identify ambassadors
35 | Social media campaign: featuring "champions" and their digital badge stories | Maximize engagement
35 | Add line to staff email signature - "Have you accepted your badge? Contact me to learn how." | Expand visibility
42 | Social media campaign: How to use your badge | Maximize engagement
45 | Follow up email to those who haven't accepted badge | Maximize engagement
60 | Badging video - include on website and social campaigns | Maximize engagement
… | …
360 | Conduct first annual earner survey to evaluate outcomes of badging program | Measure outcomes
370 | Identify earners to interview and feature | Measure outcomes
390 | Create blog post/case study highlighting career outcomes and success stories | Promote outcomes
400 | Publish program outcomes on website and social, weave into other marketing content | Promote outcomes
… | … | Keep going!